RAMBELENERGY.COM

Phase 1 MVP Scope Document

Professional Energy Analysis & Sustainability Intelligence Platform

| Project | RamBelEnergy.com - Phase 1 Lean MVP |
| --- | --- |
| Primary Focus | Algeria-Europe energy relations and sustainability intelligence |
| Estimated Timeline | 4 weeks from approved kickoff and content availability |
| Project Budget | USD 1,000, excluding third-party and operating costs |
| Document Status | Scope baseline for client review and approval |

Scope principle: Think big, start humble, build a solid base.

Document Control

| Item | Details |
| --- | --- |
| Purpose | Define the agreed Phase 1 MVP boundaries, deliverables, exclusions, acceptance criteria, and responsibilities. |
| Reference Basis | Approved Phase 1 MVP structure and project direction provided for RamBelEnergy.com. |
| Audience | Client/project owner and development team. |
| Scope Control | Work outside this document requires prioritization, written approval, and possible budget/timeline adjustment. |

Contents

1. Project Overview and Objectives

2. MVP Success Criteria

3. Scope Included in Phase 1

4. Functional Requirements and Acceptance Criteria

5. Technical Scope and Architecture

6. Content, Client Inputs and Responsibilities

7. Scope Exclusions and Change Control

8. Timeline, Milestones and Delivery

9. Commercial Scope and Assumptions

10. Future Phase Roadmap

11. Sign-off

1. Project Overview and Objectives

RamBelEnergy.com will be developed as a professional, research-oriented digital platform focused on Algeria-Europe energy relations and sustainability intelligence. Phase 1 is a lean MVP designed to establish credibility, publish key content, and validate an initial AI-assisted experience without attempting to deliver a full SaaS or knowledge-base product.

1.1 Objectives

Present Mr. Ramdane as a credible journalist, PhD holder, analyst, and subject-matter voice.

Publish energy analysis, research, and publication references in a clear institutional format.

Highlight strategic Algeria-Europe energy topics, including the Nigeria-Algeria-Europe pipeline theme.

Introduce limited AI summarization and an assistant prototype as an early product preview.

Establish a clean technical base that can be expanded into AI/RAG and SaaS features in later phases.

MVP Boundary Phase 1 delivers a credible starter platform and controlled AI prototype. It does not deliver a fully sourced AI knowledge base, automated monitoring platform, or subscription-based SaaS product.

1.2 Platform Positioning and Design Direction

The platform should feel professional, institutional, clean, credible, and content-driven, with visual direction inspired by a research-centre style such as Ifri - Center for Energy & Climate. Design decisions should support trust, readability, and Mr. Ramdane's professional reputation.

2. MVP Success Criteria

| Success Area | Phase 1 Outcome |
| --- | --- |
| Professional Presence | Public-facing pages clearly communicate platform focus, expertise, profile, and mission. |
| Content Publishing | Admin can create, edit, and delete articles and manage research/publication entries. |
| Strategic Topic Coverage | Homepage and content structure support Algeria-Europe energy and pipeline-focused narratives. |
| AI Prototype | Selected/manual text can be processed securely for basic summarization or a simple assistant response. |
| Operational Launch | Responsive application is deployed with source code and basic handover documentation delivered. |
| Controlled Scope | Excluded advanced features remain outside the 4-week / USD 1,000 delivery unless approved separately. |

3. Scope Included in Phase 1

3.1 Lightweight Documentation

Documentation is intentionally concise and practical, sufficient to align expectations and reduce scope creep.

MVP Scope Document

Simple Requirement Document

Simple System Architecture

4-Week Timeline and Milestones

Basic Handover Notes

3.2 Public Website

| Page / Section | Included Content |
| --- | --- |
| Homepage | Hero, platform mission, featured analysis, Algeria-Europe focus, pipeline highlight, research preview, AI/search future preview, contact/call-to-action. |
| About / Profile | Mr. Ramdane's professional profile, journalism/academic/analyst identity, platform mission and vision. |
| News / Analysis | Article listing, basic categories, structured browsing presentation. |
| Article Detail | Title, author, publication date, article body, and source/reference link where provided. |
| Research / Publication | Publication listing/cards with external links or file references where provided. |

3.3 Basic CMS / Admin

Phase 1 includes a custom lightweight CMS intended for controlled content management rather than complex editorial workflows.

Secure admin login

Create, edit, and delete articles

Manage research/publication items

Manage essential platform content required for the agreed public pages

3.4 Basic AI Feature

Basic AI summarization from manually supplied or selected article content.

Simple AI assistant prototype using an energy/sustainability-oriented prompt direction.

Secure server-side request handling so AI provider keys are not exposed in the browser.

AI output presented as assistance/preview content, not authoritative or fully sourced research output.

AI/Search Preview Section The public-facing concept “Ask about Algeria-Europe Energy” may appear as a roadmap/coming-next section in Phase 1. Its full source-grounded knowledge-base functionality is reserved for a later phase.

3.5 Responsive Delivery and Deployment

Responsive layout for common desktop and mobile screen sizes.

Deployment of frontend to Vercel and backend/database/auth/storage services to Supabase Cloud.

Environment variable configuration for sensitive credentials.

Source code and basic handover notes on delivery.

4. Functional Requirements and Acceptance Criteria

| ID | Requirement | Acceptance Criteria |
| --- | --- | --- |
| FR-01 | Homepage | Displays approved hero, mission, featured/strategic topic blocks, publication preview, AI preview and CTA content. |
| FR-02 | Profile page | Displays approved biography and platform vision content supplied by the client. |
| FR-03 | Analysis listing | Published articles are visible in a structured list and can use agreed basic categories. |
| FR-04 | Article detail | A selected article displays its core metadata, body content and optional source link. |
| FR-05 | Research/publication | Approved publication records can be shown as cards/list entries with reference links or file reference. |
| FR-06 | Admin authentication | Only authenticated admin access can reach content-management functionality. |
| FR-07 | Article management | Admin can create, update and delete article records that display correctly on public pages. |
| FR-08 | Publication management | Admin can create, update and remove publication/research items. |
| FR-09 | AI summarization | User/admin-supplied content can be sent through a secure backend and a basic generated summary is displayed. |
| FR-10 | Assistant prototype | A limited prompt-based assistant interaction can return an AI-generated response for supported input. |
| FR-11 | Deployment | Approved build is accessible in production and configuration notes are supplied. |

5. Technical Scope and Architecture

5.1 Recommended Technology Stack

| Layer | Technology / Responsibility |
| --- | --- |
| Frontend | Next.js, React and Tailwind CSS for public site and admin UI. |
| Backend | Next.js API routes/server actions and/or Supabase Edge Functions where appropriate. |
| Database | Supabase PostgreSQL for articles, publications and essential CMS content. |
| Authentication | Supabase Auth for admin login and protected access. |
| Storage | Supabase Storage for applicable uploaded assets or publication references. |
| AI Integration | OpenAI API or OpenRouter API, called only through a secure backend layer. |
| Deployment | Vercel frontend deployment and Supabase Cloud services. |

5.2 Simplified Architecture Flow

Visitor/Admin accesses the platform through the web application.

Next.js delivers public pages, admin CMS interfaces and AI prototype UI.

Backend/API layer validates requests and interacts with Supabase and the AI provider.

Supabase provides authentication, PostgreSQL data storage and file storage as required.

AI provider processes approved/manual text for summarization or limited assistant output.

Production delivery uses Vercel and Supabase Cloud.

Development approach: local-first setup using Next.js locally and local Supabase services through Docker where feasible; AI API calls continue to require internet connectivity.

6. Content, Client Inputs and Responsibilities

| Party | Responsibilities / Required Inputs |
| --- | --- |
| Client / Content Owner | Supply approved biography, mission statements, articles, publication details, branding/logo assets, contact details, source links, and approval feedback in a timely manner. |
| Development Team | Design and implement the agreed MVP, configure core services, protect secrets, perform basic testing, deploy, and provide handover materials. |
| Joint Review | Confirm page content, strategic messaging, acceptable AI prototype behaviour, final launch readiness, and any change requests. |

Content Dependency The 4-week timeline assumes the required text, assets, references and feedback are provided without material delay. Content research, translation or legal verification is not implicitly included unless agreed in writing.

7. Scope Exclusions and Change Control

7.1 Explicitly Not Included in Phase 1

Full RAG workflow, vector database/pgvector, document indexing or PDF Q&A.

Automated news crawling, large-scale source monitoring or real-time energy data APIs.

Advanced dashboards, interactive energy map, ESG/carbon analytics or predictive AI.

Subscriptions, billing, premium/member access, enterprise accounts or full SaaS automation.

Full multilingual workflow or advanced AI translation.

Mobile application or complex user dashboard.

Third-party operating expenses, premium tools, premium data providers, paid assets or paid translation.

7.2 Potential Additions Requiring Separate Approval

The following ideas may be valuable, but they are not considered included unless formally prioritized and approved as a change to this scope:

| Potential Addition | Scope Consideration |
| --- | --- |
| Tourism in Algeria Sahara content section | May broaden the platform away from the initial energy-intelligence focus; suitable for a future supporting content stream unless strategically justified. |
| Energy/government company logo showcase | Requires purpose clarification, layout definition, client-supplied/authorized brand assets, and consideration of endorsement/usage implications. |
| Summarizing or curating multiple externally provided articles | Adds editorial/research review effort and should be scoped by article quantity, approval process and publishing responsibility. |

7.3 Change Control Process

Any request outside the included deliverables is documented as a change request.

The change is reviewed for impact on timeline, budget, architecture and launch priorities.

Work proceeds only after written approval of the revised scope, cost and/or delivery timing.

When the budget or timeline is fixed, new requests may require replacement or removal of an existing item.

8. Timeline, Milestones and Delivery

| Week | Focus | Deliverables |
| --- | --- | --- |
| Week 1 | Scope, documentation and setup | Final scope confirmation; requirements; architecture; layout direction; repository; local setup; initial database structure. |
| Week 2 | Core website development | Homepage; profile; analysis listing; article detail; research/publication page; basic responsive layout. |
| Week 3 | CMS and basic AI | Admin/CMS; article and publication management; AI summarization; assistant prototype; secure AI backend; admin security basics. |
| Week 4 | Polish, testing and launch | UI polish; responsive testing; bug fixing; sample content setup; deployment; handover notes; source-code handover; final review. |

8.1 Delivery Workflow

Source code maintained in GitHub, ideally under client ownership, with stable and development branches as appropriate.

Preview deployments may be used during development for review.

Progress update and review are conducted at key milestones.

Production deployment follows final review and approved launch readiness.

9. Commercial Scope and Assumptions

| Item | Agreement Basis |
| --- | --- |
| Project budget | USD 1,000 for the focused Phase 1 MVP scope defined in this document. |
| Excluded costs | Domain, premium hosting plans, paid AI API consumption, paid tools/data/assets/translation, and other external operating costs. |
| Timeline basis | 4 weeks, contingent on timely inputs, decisions and controlled scope. |
| Payment suggestion | 50% at kickoff; 30% after core website and CMS; 20% at final deployment and handover. |

9.1 Delivery Package

| Category | Deliverables |
| --- | --- |
| Documentation | MVP scope, simple requirements, simple system architecture, timeline/milestones and basic handover notes. |
| Technical | Next.js application, Supabase configuration, admin login, basic CMS, public pages, AI summarization, assistant prototype, responsive UI and deployment. |
| Handover | Source code, repository/deployment access as applicable, environment setup notes and basic admin usage notes. |

10. Future Phase Roadmap

The architecture and presentation established in Phase 1 should enable later expansion, subject to separate discovery, scope and budget approval.

AI/RAG knowledge base for “Ask about Algeria-Europe Energy”.

Trusted-source ingestion, document indexing, embeddings and vector search.

PDF Q&A and source-based AI answers with references.

Multilingual AI processing, including Arabic, English, Italian, Spanish and French support.

Advanced dashboards, interactive energy map and real-time data integrations.

Automated monitoring, premium/member access, enterprise functionality and AI-generated reports.

11. Sign-off

Approval of this document confirms the Phase 1 MVP baseline. Work beyond this scope is subject to the change-control process described above.

| Client / Project Owner | Development Provider |
| --- | --- |
| Name: Ramdane Belamri | Name: Moh Puji Junaedi |
| Signature: ___________________________ | Signature: ___________________________ |
| Date: 25/05/2026 | Date: 25/05/2026 |